## Group A (471 Winter 2020)
Activity | Task | Subtask | Subtask description | Status | Estimation | Release | Personas
911 Phone Simulation Use | Calling | Compile requirements and note | Compile notes from initial presentation and requirements document, pick out important points and key ideas. | Done |  | Release 0.01 MVP | Kids
911 Phone Simulation Use | Calling | Setup USM and MVP | Set up USM and MVP(releases) to document workflow and requirements | Done |  | Release 0.01 MVP | Kids
911 Phone Simulation Use | Calling | Document Problem Definition | Create a Problem definition document to guide rationale, requirements, needs and stakeholders. It contains: Problem definition, Project Vision, Rationale, Stakeholders, North star customer, Assumptions, Constraints, Customer ecosystem map(s) High level cutomer needs | Done |  | Release 0.01 MVP | Kids
911 Phone Simulation Use | Calling | Lofi prototype of web application |  | Done |  | Release 0.02 MVP | Kids
911 Phone Simulation Use | Calling | Lofi prototype of Phone Simlutation |  | Done |  | Release 0.02 MVP | Kids
911 Phone Simulation Use | Calling | Hifi prototype of web application |  | Done |  | Release 0.03 MVP | Kids
911 Phone Simulation Use | Calling | Hifi prototype of Phone simulation |  | Done |  | Release 0.03 MVP | Kids
911 Phone Simulation Use | Calling | Create Phone Project |  | Done |  | Release 1 MVP | Kids
911 Phone Simulation Use | Calling | Create interface for call |  | Done |  | Release 1 MVP | Kids
911 Phone Simulation Use | Calling | Create Readme/installation files |  | Done |  | Release 1.1 MVP | Kids
911 Phone Simulation Use | Calling | Create Project Presentation |  | Done |  | Release 1.1 MVP | Kids
911 Phone Simulation Use | Calling | Finish Documentation |  | Done |  | Release 1.1 MVP | Kids
911 Phone Simulation Use | Calling | Update navigation to practice IOS and Android navigation |  | Todo |  | Release 2 MVP Post Launch | Kids
911 Phone Simulation Use | Navigation | Create questions and ideas | Create questions and ideas to further improve requirement and need definitions, check design ideas and constraints etc | Done |  | Release 0.01 MVP | Kids
911 Phone Simulation Use | Navigation | Develop Empathy Maps for stake holders | Create Empathy Maps for stakeholders to allow for better understanding of motivation, needs and requirements: Candace (Fire & Protective Services Educators) Kids FireFighters (Tim/UofR) (Students (us)) | Done |  | Release 0.01 MVP | Kids
911 Phone Simulation Use | Navigation | Adjust project definition |  | Done |  | Release 0.02 MVP | Kids
911 Phone Simulation Use | Navigation | Update problem definition |  | Done |  | Release 0.03 MVP | Kids
911 Phone Simulation Use | Navigation | Add 911 Call Script |  | Done |  | Release 1 MVP | Kids
911 Phone Simulation Use | Navigation | Add interface navigation |  | Done |  | Release 1 MVP | Kids
911 Phone Simulation Use | Navigation | Add Tips and Reinforcement |  | Done |  | Release 1 MVP | Kids
911 Phone Simulation Use | Navigation | Style Tips & Reinforcement |  | Done |  | Release 1 MVP | Kids
911 Phone Simulation Use | Navigation | Update project documents |  | Done |  | Release 1.1 MVP | Kids
911 Phone Simulation Use | Navigation | Create solution link |  | Done |  | Release 1.1 MVP | Kids
911 Phone Simulation Use | Navigation | Add Information Tab |  | Todo |  | Release 2 MVP Post Launch | Kids
911 Phone Simulation Use | Navigation | Update Sounds used |  | Todo |  | Release 2 MVP Post Launch | Kids
Fire Education Application Connection | Guest | Add cookies to remember guest sessions |  | Todo |  | Release 3 MVP | Kids Parents
Fire Education Application Fire Escape Plan | Create | Add step by step escape instruction generation |  | Todo |  | Release 2 MVP Post Launch | Kids Parents
Fire Education Application Fire Escape Plan | Create | Add House plan creation |  | Todo |  | Release 3 MVP | Kids Parents
Fire Education Application Fire Escape Plan | Save | Add drawing functionality |  | Todo |  | Release 2 MVP Post Launch | Kids Parents
Fire Education Application Fire Escape Plan | Save | Add Save drawing functionality |  | Todo |  | Release 3 MVP | Kids Parents
Fire Education Application Fire Escape Plan | Export/Print | Add Drawing export functionality |  | Todo |  | Release 3 MVP | Kids Parents
Fire Education Application Fire Escape Plan | Export/Print | Add instructions for specific rooms on export |  | Todo |  | Release 5 | Kids Parents
Fire Education Application Education Material | Programming | Add fire education information tabs |  | Todo |  | Release 3 MVP | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Programming | Add Activities for kids on fire education |  | Todo |  | Release 3 MVP | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Programming | Add new games to practice fire education |  | Todo |  | Release 4 | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Programming | Add Review information and educational materials |  | Todo |  | Release 5 | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Add Maze functionality |  | Todo |  | Release 2 MVP Post Launch | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Auto Generate Mazes |  | Todo |  | Release 3 MVP | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Add hints and help to game |  | Todo |  | Release 3 MVP | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Add ability to play with custom blueprint/fire escape plan |  | Todo |  | Release 4 | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Add difficulty selector |  | Todo |  | Release 5 | Kids Fire & Protection Services Parents
Note on A2: To help educate children in fire safety, calling 911 is part of the scenario. Currently the system use old touch tone phones connected together to allow for calling without calling 911. However, the children have not used the phones before and have to get them explained each use which takes away from the learning experience. <Application> In order to practice calling 911, the kids open the App and call 911, it automatically connects to another phone running the App and allows for practice without actually calling 911.
Note on B2: As a kid, I want a phone that is familiar in looks and use and easy to use so that I can practice calling 911 realistically.
Note on B15: As a firefighter, I want kids to identify the phone app and call 911 in a safe way so that they have practice and know what to do in the event of a fire.
Note on A27: To help communities become safer, in addition to fire education for kids, parents are also given information. This information is sent home in letter form and is not a reliable form of communication. Fire safety and a fire escape plan are sent home to be completed, if not read or completed, fire safety is lessened. <Application> In order to increase kids' education, an application will allow parents and kids to easily access information regarding fire safety. They can sign up or login to the application to save progress and files, or access the application as a guest.
Note on B27: As a user, I want to be able to use the application as a gues so that I do not have to sign up or login.
Note on A28: To help communities become safer, in addition to fire education for kids, parents are also given information. This information is sent home in letter form and is not a reliable form of communication. Fire safety and a fire escape plan are sent home to be completed, if not read or completed, fire safety is lessened. <Application> In order to increase kids' education, an application will allow parents and kids to easily access information regarding fire safety. In addition, the application allows for fire safety plans to be drawn up.
Note on B28: As a user, I want to be able to create a new fire escape plan so that I can have an escape plan for my house.
Note on B30: As a user, I want to be able to save fire escape plans so that they can be edited or accessed in the future.
Note on B32: As a user, I want to export or print the fire escape plans so that there can be a physical copy of the escape plan.
Note on A34: To help communities become safer, in addition to fire education for kids, parents are also given information. This information is sent home in letter form and is not a reliable form of communication. Fire safety and a fire escape plan are sent home to be completed, if not read or completed, fire safety is lessened. <Application> In order to increase kids' education, an application will allow parents and kids to easily access information regarding fire safety. The application provides information and programming for children and parents, remembering progress from activities.
Note on B34: As a user, I want to access information on fire education and prevention so that my family can be more informed.

## Releases
Name | Goal | Start date | Release date | Is released | Is archived
Release 0.01 MVP |  |  |  | False | False
Release 0.02 MVP |  |  |  | False | False
Release 0.03 MVP |  |  |  | False | False
Release 1 MVP |  |  |  | False | False
Release 1.1 MVP |  |  |  | False | False
Release 2 MVP Post Launch |  |  |  | False | False
Release 3 MVP |  |  |  | False | False
Release 4 |  |  |  | False | False
Release 5 |  |  |  | False | False

## Personas
Persona | Group | Details | Picture
Fire & Protection Services |  | Fire & Protection Services and Firefighters | 0
Kids | User |  | 0
Parents | User |  | 0