## Group A (471 Winter 2020)
Kids |  | Kids,Parents | Kids,Parents |  |  | Kids,Fire & Protection Services,Parents
911 Phone Simulation Use |  | Fire Education Application Connection | Fire Education Application Fire Escape Plan |  |  | Fire Education Application Education Material
Calling | Navigation | Guest | Create | Save | Export/Print | Programming | Fire Escape Game
Release 0.01 MVP
Compile requirements and note | Create questions and ideas
Setup USM and MVP | Develop Empathy Maps for stake holders
Document Problem Definition
Release 0.02 MVP
Lofi prototype of web application | Adjust project definition
Lofi prototype of Phone Simlutation
Release 0.03 MVP
Hifi prototype of web application | Update problem definition
Hifi prototype of Phone simulation
Release 1 MVP
Create Phone Project | Add 911 Call Script
Create interface for call | Add interface navigation
Add Tips and Reinforcement
Style Tips & Reinforcement
Release 1.1 MVP
Create Readme/installation files | Update project documents
Create Project Presentation | Create solution link
Finish Documentation
Release 2 MVP Post Launch
Update navigation to practice IOS and Android navigation | Add Information Tab |  | Add step by step escape instruction generation | Add drawing functionality |  |  | Add Maze functionality
Update Sounds used
Release 3 MVP
|  | Add cookies to remember guest sessions | Add House plan creation | Add Save drawing functionality | Add Drawing export functionality | Add fire education information tabs | Auto Generate Mazes
[6 empty] | Add Activities for kids on fire education | Add hints and help to game
Release 4
[6 empty] | Add new games to practice fire education | Add ability to play with custom blueprint/fire escape plan
Release 5
[5 empty] | Add instructions for specific rooms on export | Add Review information and educational materials | Add difficulty selector