## Group A (471 Winter 2020)
Fire & Protection Services |  |  |  | Kids |  | Kids,Parents |  |  | Kids,Parents |  |  | Kids,Fire & Protection Services,Parents
911 Phone Simulation App Setup |  |  |  | 911 Phone Simulation Use |  | Fire Education Application Connection |  |  | Fire Education Application Fire Escape Plan |  |  | Fire Education Application Education Material
Signup | Login | Phone Connection | Account setup | Calling | Navigation | Sign up | Login | Guest | Create | Save | Export/Print | Programming | Fire Escape Game
Release 0.01 MVP
Compile requirements and note | Develop Empathy Maps for stake holders | Document Problem Definition | Create Affinity Diagram
Create questions and ideas | Setup USM and MVP
Release 0.02 MVP
Lofi prototype of Phone Simlutation | Lofi prototype of web application | Adjust project definition | Gather additional requirements
Release 0.03 MVP
Hifi prototype of Phone simulation | Hifi prototype of web application | Update problem definition
Release 1
Create Phone Project |  | Add call functionality between devices
Install necessary libraries
Release 2
Create user system to allow specified role | Create Login system for users |  | Create Account setup for caller and receiver | Create interface for call | Add interface navigation | Create Web Application | Install Web Application dependencies |  | Add drawing functionality |  |  |  | Add Maze functionality
Release 3
[6 empty] | Add User system for web app |  |  | Add House plan creation | Add Save drawing functionality | Add Drawing export functionality | Add fire education information tabs | Auto Generate Mazes
[12 empty] | Add Activities for kids on fire education | Add hints and help to game
Release 4 MVP
Create Readme/installation files | Finish Documentation | Update project documents
Create Project Presentation | Create solution link
Release 5 MVP Post Launch
[5 empty] | Update navigation to practice IOS and Android navigation |  |  |  | Add step by step escape instruction generation |  |  | Add new games to practice fire education | Add ability to play with custom blueprint/fire escape plan
Add save progress functionality
Release 6 MVP
[8 empty] | Add cookies to remember guest sessions |  |  | Add instructions for specific rooms on export | Add Review information and educational materials | Add difficulty selector