## Group A (471 Winter 2020)
Activity | Task | Subtask | Subtask description | Status | Estimation | Release | Personas
911 Phone Simulation App Setup | Signup | Compile requirements and note | Compile notes from initial presentation and requirements document, pick out important points and key ideas. | Done |  | Release 0.01 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Signup | Create questions and ideas | Create questions and ideas to further improve requirement and need definitions, check design ideas and constraints etc | Done |  | Release 0.01 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Signup | Lofi prototype of Phone Simlutation |  | Done |  | Release 0.02 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Signup | Hifi prototype of Phone simulation |  | Todo |  | Release 0.03 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Signup | Create Phone Project |  | Todo |  | Release 1 | Fire & Protection Services
911 Phone Simulation App Setup | Signup | Install necessary libraries |  | Todo |  | Release 1 | Fire & Protection Services
911 Phone Simulation App Setup | Signup | Create user system to allow specified role | Role specification for caller or callee | Todo |  | Release 2 | Fire & Protection Services
911 Phone Simulation App Setup | Signup | Create Readme/installation files |  | Todo |  | Release 4 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Signup | Create Project Presentation |  | Todo |  | Release 4 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Login | Develop Empathy Maps for stake holders | Create Empathy Maps for stakeholders to allow for better understanding of motivation, needs and requirements: Candace (Fire & Protective Services Educators) Kids FireFighters (Tim/UofR) (Students (us)) | Done |  | Release 0.01 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Login | Setup USM and MVP | Set up USM and MVP(releases) to document workflow and requirements | Done |  | Release 0.01 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Login | Lofi prototype of web application |  | Done |  | Release 0.02 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Login | Hifi prototype of web application |  | Todo |  | Release 0.03 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Login | Create Login system for users |  | Todo |  | Release 2 | Fire & Protection Services
911 Phone Simulation App Setup | Login | Finish Documentation |  | Todo |  | Release 4 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Login | Create solution link |  | Todo |  | Release 4 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Phone Connection | Document Problem Definition | Create a Problem definition document to guide rationale, requirements, needs and stakeholders. It contains: Problem definition, Project Vision, Rationale, Stakeholders, North star customer, Assumptions, Constraints, Customer ecosystem map(s) High level cutomer needs | Done |  | Release 0.01 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Phone Connection | Adjust project definition |  | Done |  | Release 0.02 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Phone Connection | Update problem definition |  | Todo |  | Release 0.03 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Phone Connection | Add call functionality between devices |  | Todo |  | Release 1 | Fire & Protection Services
911 Phone Simulation App Setup | Phone Connection | Update project documents |  | Todo |  | Release 4 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Account setup | Create Affinity Diagram |  | Done |  | Release 0.01 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Account setup | Gather additional requirements |  | Done |  | Release 0.02 MVP | Fire & Protection Services
911 Phone Simulation App Setup | Account setup | Create Account setup for caller and receiver |  | Todo |  | Release 2 | Fire & Protection Services
911 Phone Simulation Use | Calling | Create interface for call |  | Todo |  | Release 2 | Kids
911 Phone Simulation Use | Navigation | Add interface navigation |  | Todo |  | Release 2 | Kids
911 Phone Simulation Use | Navigation | Update navigation to practice IOS and Android navigation |  | Todo |  | Release 5 MVP Post Launch | Kids
Fire Education Application Connection | Sign up | Create Web Application |  | Todo |  | Release 2 | Kids Parents
Fire Education Application Connection | Sign up | Add User system for web app |  | Todo |  | Release 3 | Kids Parents
Fire Education Application Connection | Login | Install Web Application dependencies |  | Todo |  | Release 2 | Kids Parents
Fire Education Application Connection | Guest | Add cookies to remember guest sessions |  | Todo |  | Release 6 MVP | Kids Parents
Fire Education Application Fire Escape Plan | Create | Add drawing functionality |  | Todo |  | Release 2 | Kids Parents
Fire Education Application Fire Escape Plan | Create | Add House plan creation |  | Todo |  | Release 3 | Kids Parents
Fire Education Application Fire Escape Plan | Create | Add step by step escape instruction generation |  | Todo |  | Release 5 MVP Post Launch | Kids Parents
Fire Education Application Fire Escape Plan | Save | Add Save drawing functionality |  | Todo |  | Release 3 | Kids Parents
Fire Education Application Fire Escape Plan | Export/Print | Add Drawing export functionality |  | Todo |  | Release 3 | Kids Parents
Fire Education Application Fire Escape Plan | Export/Print | Add instructions for specific rooms on export |  | Todo |  | Release 6 MVP | Kids Parents
Fire Education Application Education Material | Programming | Add fire education information tabs |  | Todo |  | Release 3 | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Programming | Add Activities for kids on fire education |  | Todo |  | Release 3 | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Programming | Add new games to practice fire education |  | Todo |  | Release 5 MVP Post Launch | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Programming | Add Review information and educational materials |  | Todo |  | Release 6 MVP | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Add Maze functionality |  | Todo |  | Release 2 | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Auto Generate Mazes |  | Todo |  | Release 3 | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Add hints and help to game |  | Todo |  | Release 3 | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Add ability to play with custom blueprint/fire escape plan |  | Todo |  | Release 5 MVP Post Launch | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Add save progress functionality |  | Todo |  | Release 5 MVP Post Launch | Kids Fire & Protection Services Parents
Fire Education Application Education Material | Fire Escape Game | Add difficulty selector |  | Todo |  | Release 6 MVP | Kids Fire & Protection Services Parents
Note on A2: To help educate children in fire safety, calling 911 is part of the scenario. Currently the system use old touch tone phones connected together to allow for calling without calling 911. <Application> Firefighters would open the application, setup two phones to connect to each other to allow for call simulation.
Note on B2: As a firefighter, I want to setup two accounts, one to send a call and another to receive a call so that two phones can be used and reliably connected.
Note on B11: As a firefighter I want two phones to be able connect so that one can call and one can receive.
Note on B18: As a Fire & Protection Services worker, I want to connect two phones so that a mock 911 call can take place.
Note on B23: As a firefighter, I want to be able to use the app on both Android and IOS and switch which phone sends or receives the call so that there is freedom with using the phones.
Note on A26: To help educate children in fire safety, calling 911 is part of the scenario. Currently the system use old touch tone phones connected together to allow for calling without calling 911. However, the children have not used the phones before and have to get them explained each use which takes away from the learning experience. <Application> In order to practice calling 911, the kids open the App and call 911, it automatically connects to another phone running the App and allows for practice without actually calling 911.
Note on B26: As a kid, I want a phone that is familiar in looks and use and easy to use so that I can practice calling 911 realistically.
Note on B27: As a firefighter, I want kids to identify the phone app and call 911 in a safe way so that they have practice and know what to do in the event of a fire.
Note on A29: To help communities become safer, in addition to fire education for kids, parents are also given information. This information is sent home in letter form and is not a reliable form of communication. Fire safety and a fire escape plan are sent home to be completed, if not read or completed, fire safety is lessened. <Application> In order to increase kids' education, an application will allow parents and kids to easily access information regarding fire safety. They can sign up or login to the application to save progress and files, or access the application as a guest.
Note on B29: As a user, I want to be able to save fire safety plans and progress so that I don't lose information when accessing the site repeatedly.
Note on B31: As a user, I want to login and access the information that is saved to my account so that fire safety plans can be started and completed at later times and progress in activities can be saved.
Note on B32: As a user, I want to be able to use the application as a gues so that I do not have to sign up or login.
Note on A33: To help communities become safer, in addition to fire education for kids, parents are also given information. This information is sent home in letter form and is not a reliable form of communication. Fire safety and a fire escape plan are sent home to be completed, if not read or completed, fire safety is lessened. <Application> In order to increase kids' education, an application will allow parents and kids to easily access information regarding fire safety. In addition, the application allows for fire safety plans to be drawn up.
Note on B33: As a user, I want to be able to create a new fire escape plan so that I can have an escape plan for my house.
Note on B36: As a user, I want to be able to save fire escape plans so that they can be edited or accessed in the future.
Note on B37: As a user, I want to export or print the fire escape plans so that there can be a physical copy of the escape plan.
Note on A39: To help communities become safer, in addition to fire education for kids, parents are also given information. This information is sent home in letter form and is not a reliable form of communication. Fire safety and a fire escape plan are sent home to be completed, if not read or completed, fire safety is lessened. <Application> In order to increase kids' education, an application will allow parents and kids to easily access information regarding fire safety. The application provides information and programming for children and parents, remembering progress from activities.
Note on B39: As a user, I want to access information on fire education and prevention so that my family can be more informed.

## Releases
Name | Goal | Start date | Release date | Is released | Is archived
Release 0.01 MVP |  |  |  | False | False
Release 0.02 MVP |  |  |  | False | False
Release 0.03 MVP |  |  |  | False | False
Release 1 |  |  |  | False | False
Release 2 |  |  |  | False | False
Release 3 |  |  |  | False | False
Release 4 MVP |  |  |  | False | False
Release 5 MVP Post Launch |  |  |  | False | False
Release 6 MVP |  |  |  | False | False

## Personas
Persona | Group | Details | Picture
Fire & Protection Services |  | Fire & Protection Services and Firefighters | 0
Kids | User |  | 0
Parents | User |  | 0